## start
Number | 4
Year | 2025
Contract name | Lyon 4_2025
Project Manage | Michael Thompson
Contract Type | Hourly Project
Project Start Date | 2025-06-16
Project End Date | 2025-09-01
Country | France

## Project Costs
Group | Cost Breakdown Progress | Budget | Cost | Budget Variance
Labor Costs | 91.67% | 65000 | 60000 | 5000
Accommodation | 100% | 15000 | 16000 | -1000
Equipment Costs | 100% | 42500 | 50000 | -7500
Transportation Costs | 100% | 8500 | 6000 | 2500
Sum |  | 131000 | 132000 | -1000

## Hourly and Rate Report
Week Number | Working Hours | Average Number of People | Work Progress | Overtime Hours
1 | 4 | 5 | 2% | 0
2 | 10 | 10 | 5% | 8
3 | 12 | 20 | 10% | 0
4 | 40 | 22 | 30% | 12
5 | 50 | 30 | 40% | 10
6 | 50 | 30 | 60% | 5
7 | 52 | 12 | 70% | 4
8 | 11 | 10 | 80% | 7
9 | 12 | 10 | 83% | 0
10 | 8 | 2 | 98% | 1
11 | 5 | 2 | 100% | 5
Sum | 254 | 153 |  | 52