## start
Number | 1
Year | 2025
Contract name | Rzeszow 1_2025
Project Manage | James Anderson
Contract Type | Hourly Project
Project Start Date | 2025-01-10
Project End Date | 2025-03-06
Country | Poland

## Project Costs
Group | Cost Breakdown Progress | Budget | Cost | Budget Variance
Labor Costs | 100% | 20000 | 22000 | -2000
Accommodation | 100% | 5000 | 4000 | 1000
Equipment Costs | 100% | 15000 | 12000 | 3000
Transportation Costs | 100% | 3000 | 5000 | -2000
Sum |  | 43000 | 43000 | 0

## Hourly and Rate Report
Week Number | Working Hours | Average Number of People | Work Progress | Overtime Hours
1 | 4 | 3 | 2% | 0
2 | 7 | 4 | 5% | 2
3 | 10 | 5 | 10% | 0
4 | 12 | 5 | 20% | 2
5 | 12 | 5 | 55% | 2
6 | 13 | 5 | 75% | 0
7 | 8 | 5 | 80% | 0
8 | 5 | 4 | 90% | 4
9 | 4 | 3 | 90% | 0
10 | 4 | 3 | 100% | 0
Sum | 79 | 42 |  | 10