## start
Number | 3
Year | 2025
Contract name | Prague 3_2025
Project Manage | Emily Johnson
Contract Type | Hourly Project
Project Start Date | 2025-06-03
Project End Date | 2025-08-05
Country | Czech Republic

## Project Costs
Group | Cost Breakdown Progress | Budget | Cost | Budget Variance
Labor Costs | 75% | 50000 | 40000 | 10000
Accommodation | 42.86% | 11000 | 7000 | 4000
Equipment Costs | 68.75% | 31500 | 24000 | 7500
Transportation Costs | 100% | 7800 | 8000 | -200
Sum |  | 100300 | 79000 | 21300

## Hourly and Rate Report
Week Number | Working Hours | Average Number of People | Work Progress | Overtime Hours
1 | 4 | 5 | 2% | 0
2 | 10 | 10 | 5% | 8
3 | 12 | 20 | 10% | 0
4 | 40 | 22 | 30% | 12
5 | 42 | 22 | 55% | 10
6 | 34 | 21 | 78% | 5
7 | 25 | 8 | 80% | 4
8 | 10 | 5 | 92% | 7
9 | 5 | 5 | 100% | 0
Sum | 182 | 118 |  | 46