## start
Number | 2
Year | 2025
Contract name | San Marino 2_2025
Project Manage | John Doe
Contract Type | Hourly Project
Project Start Date | 2025-03-10
Project End Date | 2025-05-28
Country | Italy

## Project Costs
Group | Cost Breakdown Progress | Budget | Cost | Budget Variance
Labor Costs | 87% | 50000 | 55000 | -5000
Accommodation | 89% | 10000 | 8500 | 1500
Equipment Costs | 83% | 30000 | 24000 | 6000
Transportation Costs | 71% | 7000 | 8000 | -1000
Sum |  | 97000 | 95500 | 1500

## Hourly and Rate Report
Week Number | Working Hours | Average Number of People | Work Progress | Overtime Hours
1 | 6 | 4 | 2% | 0
2 | 20 | 6 | 5% | 3
3 | 20 | 15 | 10% | 0
4 | 30 | 15 | 30% | 10
5 | 24 | 15 | 55% | 10
6 | 33 | 12 | 78% | 6
7 | 28 | 12 | 80% | 5
8 | 18 | 10 | 92% | 5
9 | 15 | 5 | 98% | 0
10 | 10 | 5 | 99% | 0
11 | 5 | 4 | 100% | 0
Sum | 209 | 103 |  | 39